## Sheet1
Task | Description / Link | Start Date | End Date | Assigned To
Redirect your users to upload to Stream (on SharePoint) | https://learn.microsoft.com/en-us/stream/streamnew/migration-settings#save-videos-to-stream-on-sharepoint |  |  | Stream Admin / SharePoint Admin
Block upload for your users, with exceptions to a few ( internal comms) | https://learn.microsoft.com/en-us/stream/streamnew/migration-settings#block-upload-for-most-users-but-allow-others |  |  | Stream Admin / SharePoint Admin
Run the Inventory Report | https://learn.microsoft.com/en-us/stream/streamnew/migration-details#stream-classic-video-report |  |  | Stream Admin / SharePoint Admin
Create a list of critical business containers. |  |  |  | Internal Comms , Stream Admin , SharePoint Admin
Decide on an approach | https://learn.microsoft.com/en-us/stream/streamnew/migration-strategies |  |  | Business decision maker
Review Guided Walkthrough for Curated Video Portal |  |  |  | Internal Comms , SharePoint Admin , Site Owners
Hold a Planning Session |  |  |  | Project Manager
Create internal help pages | https://github.com/jasonwbaxter/StreamClassicMigration |  |  | SharePoint Admin
Communicate the migration plan |  |  |  | Adoption & Change Management
Use example messages | https://learn.microsoft.com/en-us/stream/streamnew/classic-to-new-adoption#example-message-ideas |  |  | Adoption & Change Management
Start Campaign of Communications to affected users | Export a list of users from the Inventory Report and supply this to Internal Comms teams / ACM Teams. |  |  | Adoption & Change Management
Send User Guides | https://aka.ms/StreamUserGuide & https://aka.ms/DiffStreamClassicToSP |  |  | Adoption & Change Management
Confirm Information Architecture for SharePoint Online & Curated Video Portals
Build curated Video Portals / Pages and Associate to a Hub Site/s
Configure webparts such as Highlighted Content , Hero , File Viewer | to build out your Topic Video Pages
Adjust metadata on the libraries accordingly to create a more dynamic experience when posting new content.
Migrate test content for each type of migration | User Containers , Orphaned Containers , M365 Groups , Company Wide Channels |  |  | Stream Admin / SharePoint Admin
Pilot with business critical containers | Containers from CEO videos, corp comms, training or product demos should first be migrated |  |  | Stream Admin / SharePoint Admin
Use Partial migration to migrate remaining content | The migration tool can either migrate complete container or just specific videos from within the container. |  |  | Stream Admin / SharePoint Admin
Assign Destinations to non auto mapped containers such as Company Wide Channels |  |  |  | Stream Admin / SharePoint Admin
Migrate in batches | Don't migrate all content at once. It's advisable to choose a batch of right size, say 500, 1000 or ever more. Resolve error in a batch before starting to migrate the next one. Use tags to choose a batch from all containers in UI |  |  | Stream Admin / SharePoint Admin
Migrate Users containers to Onedrive |  |  |  | Stream Admin / SharePoint Admin
Migrate M365 containers to M365Groups |  |  |  | Stream Admin / SharePoint Admin
Migrate Channel Wide Containers to Curated Video portals |  |  |  | Stream Admin / SharePoint Admin
Track migration progress via Migration summary report
Download reports for longer review after 30 days.